## Sheet1
week7
Bicycle Manajement System |  | Week 1 | Week 2 |  | Week 3 | week4 |  | week5 | week6 |  |  | week8 | week-9 |  | Week-10 | Week-11 | Week-12 | Week-13 | Week-14 |  | Week-15 | Week-16 | Week-17 | Week-18 | Week-19 | Week-20 | Week-21
1.1.1 | Project Managements
Project Planning
Task Management
Team Communication
Resource Allocation
Cost & Schedule Management
u
1.1.2 | System Design
Requirements Gathering
System Architecture Design
DataBase Design
User interface Design
Payment integration Planning
u
1.1.3 | Software Development
Web interface
Mobile interface Design
Server side Development
Datababe Integration
QR code payment Integration
Online payment Gateway
u
1.1.4 | Teating
Unit testing
System integration testing
User acceptance testing
Bug fixing & debugging
u
1.1.5 | Development
System installation
Server setup & deployment
User Training
Documentation for end User
u
1.1.6 | Support & maintance
System monitoring
performance Optimization
Bug tracing & resolution
Future Update & Enhancements